## FAS Centralization
Schedule for Centralization of Construction Payments to the FSC
Color Key: |  | Parent Facility | Consolidated VISN |  |  | As of 8/8/2007
VISN | Station | Name | Vendor Notificaton Date | OLCS Training Date | OLCS Training Time | Conversion Date
22 | 593 | Las Vegas, NV | 2005-12-20 | 2006-01-10 | 2:30-4:30pm CST | Completed
| 600 | Long Beach, CA | 2005-12-20 | 2006-01-10 | 2:30-4:30pm CST | Completed
| 605 | Loma Linda, CA | 2005-12-20 | 2006-01-10 | 2:30-4:30pm CST | Completed
| 664 | San Diego, CA | 2005-12-20 | 2006-01-10 | 2:30-4:30pm CST | Completed
| 665 | Sepulveda, CA | 2005-12-20 | 2006-01-10 | 2:30-4:30pm CST | Completed
| 691 | West Los Angeles, CA | 2005-12-20 | 2006-01-10 | 2:30-4:30pm CST | Completed
| 762 | West Los Angeles, CA | 2005-12-20 | 2006-01-10 | 2:30-4:30pm CST | Completed
08 | 516 | Bay Pines, Fl | 2006-01-11 | 2006-01-25 | 10:00-12:00 pm CST | Completed
| 546 | Miami, FL | 2006-01-11 | 2006-01-25 | 10:00-12:00 pm CST | Completed
| 548 | Palm Beach County, FL | 2006-01-11 | 2006-01-25 | 10:00-12:00 pm CST | Completed
| 573 | Gainesville, FL | 2006-01-11 | 2006-01-25 | 10:00-12:00 pm CST | Completed
| 594 | Lake City, FL | 2006-01-11 | 2006-01-25 | 10:00-12:00 pm CST | Completed
| 672 | San Juan, PR | 2006-01-11 | 2006-01-25 | 10:00-12:00 pm CST | Completed
| 673 | Tampa, FL | 2006-01-11 | 2006-01-25 | 10:00-12:00 pm CST | Completed
99 | 764 | Murfreesboro, TN | 2006-01-11 | 2006-01-25 | 10:00-12:00 pm CST | Completed
| 741 | Denver, CO | 2006-01-11 | 2006-01-25 | 10:00-12:00 pm CST | Completed
| 742 | Atlanta, GA | 2006-01-11 | 2006-01-25 | 10:00-12:00 pm CST | Completed
| 761 | Bedford, MA | 2006-01-11 | 2006-01-25 | 10:00-12:00 pm CST | Completed
| 776 | Brecksville, OH | 2006-01-11 | 2006-01-25 | 10:00-12:00 pm CST | Completed
05 | 511 | Baltimore, MD | 2006-01-11 | 2006-01-25 | 10:00-12:00 pm CST | Completed
| 512 | Baltimore, MD | 2006-01-11 | 2006-01-25 | 10:00-12:00 pm CST | Completed
| 613 | Martinsburg, WV | 2006-01-11 | 2006-01-25 | 10:00-12:00 pm CST | Completed
| 688 | Washington, DC | 2006-01-11 | 2006-01-25 | 10:00-12:00 pm CST | Completed
| 792 | Baltimore, MD | 2006-01-11 | 2006-01-25 | 10:00-12:00 pm CST | Completed
12 | 537 | Chicago, IL | 2006-01-24 | 2006-02-01 | 9:00-12:00 pm CST | Completed
| 556 | North Chicago, IL | 2006-01-24 | 2006-02-01 | 9:00-12:00 pm CST | Completed
| 578 | Hines. IL | 2006-01-24 | 2006-02-01 | 9:00-12:00 pm CST | Completed
| 585 | Iron Mountain, MI | 2006-01-24 | 2006-02-01 | 9:00-12:00 pm CST | Completed
| 607 | Madison, WI | 2006-01-24 | 2006-02-01 | 9:00-12:00 pm CST | Completed
| 676 | Tomah, WI | 2006-01-24 | 2006-02-01 | 9:00-12:00 pm CST | Completed
| 695 | Wood, WI | 2006-01-24 | 2006-02-01 | 9:00-12:00 pm CST | Completed
| 765 | Hines, IL | 2006-01-24 | 2006-02-01 | 9:00-12:00 pm CST | Completed
18 | 501 | Albuquerque, NM | 2006-01-24 | 2006-02-01 | 9:00-12:00 pm CST | Completed
| 504 | Amarillo, TX | 2006-01-24 | 2006-02-01 | 9:00-12:00 pm CST | Completed
| 519 | Big Spring, TX | 2006-01-24 | 2006-02-01 | 9:00-12:00 pm CST | Completed
| 644 | Phoenix, AZ | 2006-01-24 | 2006-02-01 | 9:00-12:00 pm CST | Completed
| 649 | Prescott, AZ | 2006-01-24 | 2006-02-01 | 9:00-12:00 pm CST | Completed
| 678 | Tucson, AZ | 2006-01-24 | 2006-02-01 | 9:00-12:00 pm CST | Completed
| 756 | El Paso, TX | 2006-01-24 | 2006-02-01 | 9:00-12:00 pm CST | Completed
21 | 570 | Fresno, CA | 2006-09-25 | 2006-10-11 | 10:00-1:00 pm CST | Completed
| 612 | Martinez, CA | 2006-09-25 | 2006-10-11 | 10:00-1:00 pm CST | Completed
| 640 | Palo Alto, CA | 2006-09-25 | 2006-10-11 | 10:00-1:00 pm CST | Completed
| 654 | Reno, NV | 2006-09-25 | 2006-10-11 | 10:00-1:00 pm CST | Completed
| 662 | San Francisco, CA | 2006-09-25 | 2006-10-11 | 10:00-1:00 pm CST | Completed
| 459 | Pacific Islands HCS, Honolulu, HI | 2006-09-25 | 2006-10-12 | 1:00-4:00 pm CST | Completed
03 | 526 | Bronx, NY | 2006-10-16 | 2006-11-01 | 8:00-11:00 am CST | Completed
| 527 | Brooklyn, NY | 2006-10-16 | 2006-11-01 | 8:00-11:00 am CST | Completed
| 533 | Castle Point, NY | 2006-10-16 | 2006-11-01 | 8:00-11:00 am CST | Completed
| 561 | East Orange, NJ | 2006-10-16 | 2006-11-01 | 8:00-11:00 am CST | Completed
| 620 | Montrose, NY | 2006-10-16 | 2006-11-01 | 8:00-11:00 am CST | Completed
| 630 | New York, NY | 2006-10-16 | 2006-11-01 | 8:00-11:00 am CST | Completed
| 632 | Northport, NY | 2006-10-16 | 2006-11-01 | 8:00-11:00 am CST | Completed
02 | 500 | Albany, NY | 2006-11-20 | 2006-12-06 | 8:00-11:00 am CST | Completed
| 514 | Bath, NY | 2006-11-20 | 2006-12-06 | 8:00-11:00 am CST | Completed
| 528 | Buffalo, NY | 2006-11-20 | 2006-12-06 | 8:00-11:00 am CST | Completed
| 532 | Canandaigua, NY | 2006-11-20 | 2006-12-06 | 8:00-11:00 am CST | Completed
| 670 | Syracuse, NY | 2006-11-20 | 2006-12-06 | 8:00-11:00 am CST | Completed
10 | 538 | Chillicothe, OH | 2007-01-08 | 2207-01-24 | 8:00-11:00 am CST | Completed
| 539 | Cincinnati, OH | 2007-01-08 | 2207-01-24 | 8:00-11:00 am CST | Completed
| 541 | Cleveland, OH | 2007-01-08 | 2207-01-24 | 8:00-11:00 am CST | Completed
| 552 | Dayton, OH | 2007-01-08 | 2207-01-24 | 8:00-11:00 am CST | Completed
| 757 | Columbus, OH | 2007-01-08 | 2207-01-24 | 8:00-11:00 am CST | Completed
19 | 436 | Ft Harrison, MT | 2007-01-29 | 2007-02-14 | 9:00-12:00 pm CST | Completed
| 442 | Cheyenne, WY | 2007-01-29 | 2007-02-14 | 9:00-12:00 pm CST | Completed
| 554 | Denver, CO | 2007-01-29 | 2007-02-14 | 9:00-12:00 pm CST | Completed
| 567 | Ft Lyon, CO | 2007-01-29 | 2007-02-14 | 9:00-12:00 pm CST | Completed
| 575 | Grand Junction, CO | 2007-01-29 | 2007-02-14 | 9:00-12:00 pm CST | Completed
| 660 | Salt Lake City, UT | 2007-01-29 | 2007-02-14 | 9:00-12:00 pm CST | Completed
| 666 | Sheridan, WY | 2007-01-29 | 2007-02-14 | 9:00-12:00 pm CST | Completed
| 791 | Denver, CO | 2007-01-29 | 2007-02-14 | 9:00-12:00 pm CST | Completed
11 | 506 | Ann Arbor, MI | 2007-02-26 | 2007-03-14 | 8:00-11:00 am CST | Completed
| 515 | Battle Creek, MI | 2007-02-26 | 2007-03-14 | 8:00-11:00 am CST | Completed
| 550 | Danville, IL | 2007-02-26 | 2007-03-14 | 8:00-11:00 am CST | Completed
| 553 | Detroit, MI | 2007-02-26 | 2007-03-14 | 8:00-11:00 am CST | Completed
| 583 | Indianapolis, IN | 2007-02-26 | 2007-03-14 | 8:00-11:00 am CST | Completed
| 610 | Marion, IN | 2007-02-26 | 2007-03-14 | 8:00-11:00 am CST | Completed
| 655 | Saginaw, MI | 2007-02-26 | 2007-03-14 | 8:00-11:00 am CST | Completed
09 | 581 | Huntington, WV | 2007-03-19 | 2007-04-04 | 9:00-12:00 pm CST | Completed
| 596 | Lexington, KY | 2007-03-19 | 2007-04-04 | 9:00-12:00 pm CST | Completed
| 603 | Louisville, KY | 2007-03-19 | 2007-04-04 | 9:00-12:00 pm CST | Completed
| 614 | Memphis, TN | 2007-03-19 | 2007-04-04 | 9:00-12:00 pm CST | Completed
| 621 | Mountain Home, TN | 2007-03-19 | 2007-04-04 | 9:00-12:00 pm CST | Completed
| 622 | Murfreesboro, TN | 2007-03-19 | 2007-04-04 | 9:00-12:00 pm CST | Completed
| 626 | Nashville, TN | 2007-03-19 | 2007-04-04 | 9:00-12:00 pm CST | Completed
01 | 402 | Togus, ME | 2007-04-09 | 2007-04-25 | 8:00-11:00 am CST | Completed
| 405 | White River Jct, VT | 2007-04-09 | 2007-04-25 | 8:00-11:00 am CST | Completed
| 518 | Bedford, MA | 2007-04-09 | 2007-04-25 | 8:00-11:00 am CST | Completed
| 523 | Boston, MA | 2007-04-09 | 2007-04-25 | 8:00-11:00 am CST | Completed
| 627 | Newington. CT | 2007-04-09 | 2007-04-25 | 8:00-11:00 am CST | Completed
| 525 | Brockton, MA | 2007-04-09 | 2007-04-25 | 8:00-11:00 am CST | Completed
| 608 | Manchester, NH | 2007-04-09 | 2007-04-25 | 8:00-11:00 am CST | Completed
| 631 | Northampton, MA | 2007-04-09 | 2007-04-25 | 8:00-11:00 am CST | Completed
| 650 | Providence, RI | 2007-04-09 | 2007-04-25 | 8:00-11:00 am CST | Completed
| 689 | West Haven, CT | 2007-04-09 | 2007-04-25 | 8:00-11:00 am CST | Completed
15 | 452 | Wichita, KS | 2007-04-30 | 2007-05-09 | 9:00-12:00 pm CST | Completed
| 543 | Columbia, MO | 2007-04-30 | 2007-05-09 | 9:00-12:00 pm CST | Completed
| 589 | Kansas City, MO | 2007-04-30 | 2007-05-09 | 9:00-12:00 pm CST | Completed
| 609 | Marion, IL | 2007-04-30 | 2007-05-09 | 9:00-12:00 pm CST | Completed
| 647 | Poplar Bluff, MO | 2007-04-30 | 2007-05-09 | 9:00-12:00 pm CST | Completed
| 657 | St Louis, MO | 2007-04-30 | 2007-05-09 | 9:00-12:00 pm CST | Completed
| 677 | Topeka, KS | 2007-04-30 | 2007-05-09 | 9:00-12:00 pm CST | Completed
| 760 | Leavenworth, KS | 2007-04-30 | 2007-05-09 | 9:00-12:00 pm CST | Completed
| 702 | Topeka, KS | 2007-04-30 | 2007-05-09 | 9:00-12:00 pm CST | Completed
| 760 | Leavenworth, KS | 2007-04-30 | 2007-05-09 | 9:00-12:00 pm CST | Completed
23 | 437 | Fargo VAMROC | 2007-05-14 | 2007-05-23 | 9:00-12:00 pm CST | Completed
| 438 | Sioux Falls VAMROC | 2007-05-14 | 2007-05-23 | 9:00-12:00 pm CST | Completed
| 555 | Des Moines, IA | 2007-05-14 | 2007-05-23 | 9:00-12:00 pm CST | Completed
| 568 | VA Black Hills HCS/Hot Springs | 2007-05-14 | 2007-05-23 | 9:00-12:00 pm CST | Completed
| 568 | VA Black Hills HCS/Fort Meade | 2007-05-14 | 2007-05-23 | 9:00-12:00 pm CST | Completed
| 579 | Hot Springs, SD | 2007-05-14 | 2007-05-23 | 9:00-12:00 pm CST | Completed
| 584 | Iowa City VAMC | 2007-05-14 | 2007-05-23 | 9:00-12:00 pm CST | Completed
| 618 | Minneapolis VAMC | 2007-05-14 | 2007-05-23 | 9:00-12:00 pm CST | Completed
| 636 | Omaha Division | 2007-05-14 | 2007-05-23 | 9:00-12:00 pm CST | Completed
| 656 | St. Cloud VAMC | 2007-05-14 | 2007-05-23 | 9:00-12:00 pm CST | Completed
| 636A4 | VA Nebraska Western Iowa HCS | 2007-05-14 | 2007-05-23 | 9:00-12:00 pm CST | Completed
| 636A6 | VA Central Iowa Health Care System | 2007-05-14 | 2007-05-23 | 9:00-12:00 pm CST | Completed
| 636A7 |  | 2007-05-14 | 2007-05-23 | 9:00-12:00 pm CST | Completed
06 | 517 | Beckley, WV | 2007-05-28 | 2007-06-06 | 8:00-11:00 am CST | Completed
| 558 | Durham, NC | 2007-05-28 | 2007-06-06 | 8:00-11:00 am CST | Completed
| 565 | Fayetteville, NC | 2007-05-28 | 2007-06-06 | 8:00-11:00 am CST | Completed
| 590 | Hampton, VA | 2007-05-28 | 2007-06-06 | 8:00-11:00 am CST | Completed
| 637 | Asheville, NC | 2007-05-28 | 2007-06-06 | 8:00-11:00 am CST | Completed
| 652 | Richmond, VA | 2007-05-28 | 2007-06-06 | 8:00-11:00 am CST | Completed
| 658 | Salem, VA | 2007-05-28 | 2007-06-06 | 8:00-11:00 am CST | Completed
| 659 | Salisbury, NC | 2007-05-28 | 2007-06-06 | 8:00-11:00 am CST | Completed
04 | 460 | Wilmington, DE | 2007-06-04 | 2007-06-20 | 8:00-11:00 am CST | Completed
| 503 | Altoona, PA | 2007-06-04 | 2007-06-20 | 8:00-11:00 am CST | Completed
| 529 | Butler, PA | 2007-06-04 | 2007-06-20 | 8:00-11:00 am CST | Completed
| 540 | Clarksburg, WV | 2007-06-04 | 2007-06-20 | 8:00-11:00 am CST | Completed
| 542 | Coatesville, PA | 2007-06-04 | 2007-06-20 | 8:00-11:00 am CST | Completed
| 562 | Erie, PA | 2007-06-04 | 2007-06-20 | 8:00-11:00 am CST | Completed
| 595 | Lebanon, PA | 2007-06-04 | 2007-06-20 | 8:00-11:00 am CST | Completed
| 642 | Philadelphia, PA | 2007-06-04 | 2007-06-20 | 8:00-11:00 am CST | Completed
| 646 | Pittsburgh, PA | 2007-06-04 | 2007-06-20 | 8:00-11:00 am CST | Completed
| 693 | Wilkes Barre, PA | 2007-06-04 | 2007-06-20 | 8:00-11:00 am CST | Completed
16 | 502 | Alexandria, LA | 2007-06-25 | 2007-07-11 | 9:00-12:00 pm CST | Completed
| 520 | Biloxi, MS | 2007-06-25 | 2007-07-11 | 9:00-12:00 pm CST | Completed
| 564 | Fayetteville, AR | 2007-06-25 | 2007-07-11 | 9:00-12:00 pm CST | Completed
| 580 | Houston, TX | 2007-06-25 | 2007-07-11 | 9:00-12:00 pm CST | Completed
| 586 | Jackson, MS | 2007-06-25 | 2007-07-11 | 9:00-12:00 pm CST | Completed
| 598 | Little Rock, AR | 2007-06-25 | 2007-07-11 | 9:00-12:00 pm CST | Completed
| 623 | Muskogee, OK | 2007-06-25 | 2007-07-11 | 9:00-12:00 pm CST | Completed
| 629 | New Orleans, LA | 2007-06-25 | 2007-07-11 | 9:00-12:00 pm CST | Completed
| 635 | Oklahoma City, OK | 2007-06-25 | 2007-07-11 | 9:00-12:00 pm CST | Completed
| 667 | Shreveport, LA | 2007-06-25 | 2007-07-11 | 9:00-12:00 pm CST | Completed
| 825 | Pineville, LA | 2007-06-25 | 2007-07-11 | 9:00-12:00 pm CST | Completed
17 | 549 | Dallas, TX | 2007-06-25 | 2007-07-11 | 9:00-12:00 pm CST | Completed
| 671 | San Antonio, TX | 2007-06-25 | 2007-07-11 | 9:00-12:00 pm CST | Completed
| 674 | Temple, TX | 2007-06-25 | 2007-07-11 | 9:00-12:00 pm CST | Completed
| 685 | Waco, TX | 2007-06-25 | 2007-07-11 | 9:00-12:00 pm CST | Completed
| 763 | Dallas, TX | 2007-06-25 | 2007-07-11 | 9:00-12:00 pm CST | Completed
20 | 463 | Anchorage, AK | 2007-07-09 | 2007-07-25 | 10:00-1:00 pm CST | Completed
| 531 | Boise, ID | 2007-07-09 | 2007-07-25 | 10:00-1:00 pm CST | Completed
| 648 | Portland, OR | 2007-07-09 | 2007-07-25 | 10:00-1:00 pm CST | Completed
| 653 | Roseburg, OR | 2007-07-09 | 2007-07-25 | 10:00-1:00 pm CST | Completed
| 663 | Seattle, WA | 2007-07-09 | 2007-07-25 | 10:00-1:00 pm CST | Completed
| 668 | Spokane, WA | 2007-07-09 | 2007-07-25 | 10:00-1:00 pm CST | Completed
| 687 | Walla Walla, WA | 2007-07-09 | 2007-07-25 | 10:00-1:00 pm CST | Completed
| 692 | White City, OR | 2007-07-09 | 2007-07-25 | 10:00-1:00 pm CST | Completed
07 | 508 | Atlanta, GA | 2007-07-16 | 2007-08-01 | 9:00-12:00 pm CST | Completed
| 509 | Augusta, GA | 2007-07-16 | 2007-08-01 | 9:00-12:00 pm CST | Completed
| 521 | Birmingham, AL | 2007-07-16 | 2007-08-01 | 9:00-12:00 pm CST | Completed
| 534 | Charleston, SC | 2007-07-16 | 2007-08-01 | 9:00-12:00 pm CST | Completed
| 544 | Columbia, SC | 2007-07-16 | 2007-08-01 | 9:00-12:00 pm CST | Completed
| 557 | Dublin, GA | 2007-07-16 | 2007-08-01 | 9:00-12:00 pm CST | Completed
| 619 | Montgomery, AL | 2007-07-16 | 2007-08-01 | 9:00-12:00 pm CST | Completed
| 679 | Tuscaloosa, AL | 2007-07-16 | 2007-08-01 | 9:00-12:00 pm CST | Completed
| 680 | Tuskegee, AL | 2007-07-16 | 2007-08-01 | 9:00-12:00 pm CST | Completed
| 742 | Atlanta, GA | 2007-07-16 | 2007-08-01 | 9:00-12:00 pm CST | Completed
| 766 | North Charleston, SC | 2007-07-16 | 2007-08-01 | 9:00-12:00 pm CST | Completed